## Master_Panel+Dev
WBS ID | Workstream | Task Name | Predecessors (WBS) | Duration | Assigned To | % Complete | Milestone | Department
C-01 | Common | Project Kick-off | - | 1 Day | PM/All | 0 | Yes | Design
C-02 | Common | URS & Scope Freeze | C-01 | 1 Day | PM/All | 0 | Yes | Design
PR-01 | Production | BOM Preparation | C-02 | 1 Day | Production | 0 | No | Design
PR-02 | Production | Technical BOM Review | PR-01 | 1 Day | Production | 0 | No | Design
PR-03 | Production | BOM Approval | PR-02 | 1 Day | PM/Production | 0 | Yes | Design
PR-04 | Production | GAD Design | PR-03 | 2 Days | Design/Production | 0 | No | Design
PR-05 | Production | GAD Approval | PR-04 | 1 Day | PM/Customer | 0 | Yes | Design
PR-06 | Production | Electrical Drawing Preparation | PR-05 | 2 Days | Electrical | 0 | No | Design
PR-07 | Production | Electrical Drawing Approval | PR-06 | 1 Day | PM/Customer | 0 | Yes | Design
PR-08 | Production | Material Procurement | PR-03 | 5 Days | Purchase | 0 | No | Design
PR-09 | Production | Material Inspection & Review | PR-08 | 1 Day | QC/Store | 0 | Yes | Production
PR-10 | Production | Panel GA Assembly | PR-09 | 2 Days | Production | 0 | No | Production
PR-11 | Production | Panel Wiring | PR-10 | 3 Days | Production | 0 | No | Production
PR-12 | Production | Labelling & Stickering | PR-11 | 1 Day | Production | 0 | No | Production
PR-13 | Production | Visual Inspection & QC | PR-12 | 1 Day | QC | 0 | Yes | Production
PG-01 | Programming | System Architecture Definition | C-02 | 1 Day | Programmer | 0 | Yes | Automation
PG-02 | Programming | Control Architecture Definition | PG-01 | 1 Day | Programmer | 0 | Yes | Automation
PG-03 | Programming | Software Architecture Definition | PG-02 | 1 Day | Programmer | 0 | No | Automation
PG-04 | Programming | PLC Programming | PG-03 | 5 Days | Programmer | 0 | No | Automation
PG-05 | Programming | HMI / SCADA Development | PG-03 | 7 Days | Programmer | 0 | No | Automation
PG-06 | Programming | Alarm & Interlock Implementation | PG-04 | 2 Days | Programmer | 0 | No | Automation
PG-07 | Programming | Communication Configuration (Drives / Fieldbus) | PG-04 | 2 Days | Programmer | 0 | No | Automation
PG-08 | Programming | Dry Run / Simulation | PG-04 | 2 Days | Programmer | 0 | Yes | Automation
PG-09 | Programming | Bug Fixing & Optimization | PG-08 | 2 Days | Programmer | 0 | No | Automation
PG-10 | Programming | Program Freeze for FAT | PG-09 | 1 Day | Programmer | 0 | Yes | Automation
J-01 | Joint | Internal FAT (Panel + Program) | PR-13, PG-10 | 2 Days | All | 0 | Yes | common
J-02 | Joint | FAT Observation Closure | J-01 | 1 Day | All | 0 | Yes | common
J-03 | Joint | Final Backup & Handover | J-02 | 1 Day | PM/Programmer | 0 | Yes | common
J-04 | Joint | Final Inspection & Testing | J-03 | 1 Day | QC/All | 0 | Yes | common
J-05 | Joint | Packing & Dispatch | J-04 | 1 Day | Dispatch | 0 | Yes | Production